## Working sheet 2014 (hidden)
Sustainable Land Management in Churia Region Nepal (GEF funded)
Year 1 (CY14) |  |  | Year 2 (CY15) |  | Year 3 (CY16) |  | Total
Budget | Expense | Spending % | Budget | Expense | Budget | Expense | Budget | Expenses | Spending %
381537.5 | 285038.04 | 74.71% | 301292.3733 | 0 | 234601.1987 | 0 | 917431.072 | 285038.04 | 31.07%
Savings from 2014
Exp Jun-Dec | 99253.17
Exp Jan-Jun | 210890.72
Total | 310143.89 | exp reported to HQ | grant and consultancy obligation
Savings | 71393.61 | 285038.04 | 25105.85 | 96499.46
2015 Budget | 397791.8333
Activities transferred to 2015 from 2014
2201 | Obligation Deductable - Grants
| WT47 |  |  |  |  | -10024 | -103.78
| WT81 |  |  |  |  | -388765.62 | -4042.69
| WT82 | [5 empty] | -0.97
| WT83 |  |  |  |  | -1781813 | -18359.25
| WU22 |  |  |  |  | -20800 | -218.99
| Total |  |  |  |  | -2201402.62 | -22725.68
2206/07 | Obligation Deductable - Consultancy
| WU62 |  |  |  |  | -150650 | -1529.91
| WV81 |  |  |  |  | -85000 | -850.26
| Total |  |  |  |  | -235650 | -2380.17
| Total of grants and consultancy | [5 empty] | -25105.85 | reconciled
Note on K9: Author: DSA, communication and monitoring visits; implementing visits For all 4 project sites and implementing partners

## Guidance
Guidance
This template serves two functions: 1) Template for drafting the Annual Work Plan and Budget (AWP&B), based on the full project workplan. The purpose of the AWP&B is to ensure that activities planned for the project year will be successful at meeting the Results Framework targets, and are budgeted correctly. 2) Tracking progress against the Work Plan and Budget and the Results Framework (RF). Formulas are built into the AWP&B and Results Framework tabs to support tracking, and this is based on an average achievement of all activities/RF targets. Progress is rated annually in the Project Progress Report – the Implementation Progress Rating corresponds to AWP&B achievement, while the Development Objective Rating corresponds to achievement against the RF.
Annual Work Plan and Budget Output tracking (light orange row in AWP&B tab): Achievement of each output should be monitored over the lifetime of the project. Only include a target if the output is expected to be achieved for the given project year. Activities: Activities should be developed based on the ProDoc and what is needed to meet the Results Framework targets. Include relevant activities related to the Gender Action Plan and Stakeholder Engagement Plan. Targets/Units: The unit description should say what exactly is being measured (e.g. # of meetings). Targets should always be numerical (e.g. 5). Work plan (timing): The time dedicated to a given activity should be noted by project quarter (or, if the team prefers, by month, though this template will need to be adjusted). Budget: The budget can be provided by output or activity, and should be based off of the submitted and approved detailed budget. At the end of the year, budget spent v. activities planned and achieved can be assessed to show variance and alignment in spending and implementation. Budget variances of 5% or more at the total component level (as approved in ProDoc) needs to be approved by the WWF GEF Agency. Project Management Costs (PMC) cannot go over the total amount approved by GEF. Results Framework Definition: This column is to define any ambiguous terms in the indicator so reviewers will interpret the RF and measure against the indicator equally. Targets: Targets should be annual and numerical where possible. Note that qualitative or multi-criteria indicators can be assessed numerically with a scorecard. Please ensure these are realistic and not aspirational.
Tracking during Implementation In the AWP&B, progress can be tracked at the end of each project year under the columns labeled “Work Plan Tracking (Column M-P).” In the Results Framework tab, track progress for the given year using the columns labeled ‘actual.’ IP Rating: The project Implementation Progress (IP) rating is determined by averaging the achievement of all activities together in the workplan. DO Rating: The project Development Objective (DO) rating is determined by averaging the percent achievement of all indicators in the RF. Please note that some indicators have multiple measurements per indicator (e.g. 1 platform established with 200 registered users and 100 KM products) and it is recommended to average the achievement of all measurements taken per indicator (E.g. 1 platform, 100 users and 20 KM products would be 100% + 50% + 20% = 56%) The snapshot tab will show a summary of progress again the AWP&B and RF over the life of the project.
Full Project Workplan The annual workplan activities and targets should align with the full project workplan, so please ensure that targets are cumulative through the end of the project and that the full suite of activities are represented. The template may need to be adjusted.
Additional Notes This completed spreadsheet will be submitted for approval of the AWP&B for planning purposes. Once the tracking aspects of the AWP&B and RF are completed, it will also be submitted and annexed to the annual Project Progress Report for reporting purposes. This template was designed for four years and three components, but please adjust this template to fit the realities of this project by inserting additional rows or columns. Please note that there are forumulas already input into the template that will need to be adjusted if you do add rows or columns.

## Snapshot
Project: [Add project title]
SNAPSHOT
Annual Work Plan Activity Tracking: Summary |  |  |  |  | Results Framework Tracking: Summary
% achievement
Component | Y1 | Y2 | Y3 | Y4 | Year | % average achievement
Component 1 | 8.333% |  |  |  | Y1 | #NAME?
Component 2 | 0% |  |  |  | Y2 | #NAME?
Component 3: M&E and KM | 0% |  |  |  | Y3 | #NAME?
PMC | 0% |  |  |  | Y4
Overall average | 2.941% |  |  |  | Y5

## AWPB Yr x
Period: Year X (dates)
| ANNUAL WORK PLAN | [10 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | ACTIVITIES |  | RESPONSIBLE | YEAR 1 TIMING |  |  |  | BUDGET | X if activity is carried over from previous year | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4
A. ACTIVITY COSTS
Component 1: [Add component text]
Outcome 1.1 [Add outcome text] |  |  |  | Q1 | Q2 | Q3 | Q4
Output 1.1.1. [Add output text] | #1 | Example | Example |  |  |  |  | 50000000 | X | # workshops | 5 | 5 | 100% | 8.333%
| #2 | [Activity] | [10 empty] | 0%
|  | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #3 | [output tracking - provide information in the following columns: responsible, unit description, target] | [10 empty] | 0%
Output 1.1.2 [Add output text, add additional lines as needed] | #1 | [Activity ] | [10 empty] | 0%
| #2 | [Activity] | [10 empty] | 0%
|  | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #3 | [output tracking] | [10 empty] | 0%
Outcome 1.2 [Add outcome text] |  |  |  | Q1 | Q2 | Q3 | Q4
Output 1.2.1.[Add output text], add additional lines as needed | #1 | [Activity] | [10 empty] | 0%
| #2 | [Activity] | [10 empty] | 0%
|  | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #3 | [output tracking] | [8 empty] | Output indicator, if applicable |  | 0%
Component 2: [Add component text]
Outcome 2.1 [Add outcome text] |  |  |  | Q1 | Q2 | Q3 | Q4
Output 2.1.1. [Add output text] | #1 | [Activity] | [10 empty] | 0% | 0%
| #2 | [Activity] | [10 empty] | 0%
|  | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #3 | [output tracking] | [8 empty] | Output indicator, if applicable |  | 0%
Output 2.1.2 [Add output text, add additional lines as needed] | #1 | [Activity ] | [10 empty] | 0%
| #2 | [Activity] | [10 empty] | 0%
|  | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #3 | [output tracking] | [8 empty] | Output indicator, if applicable |  | 0%
Outcome 2.2 [Add outcome text] |  |  |  | Q1 | Q2 | Q3 | Q4
Output 2.2.1.[Add output text, add additional lines as needed] | #1 | [Activity] | [10 empty] | 0%
| #2 | [Activity] | [10 empty] | 0%
|  | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #3 | [output tracking] | [8 empty] | Output indicator, if applicable |  | 0%
Component 3: M&E
Outcome 3.1 [Add outcome text] |  |  |  | Q1 | Q2 | Q3 | Q4
Output 3.1.1. [Add output text, add additional lines as needed] | #1 | 6 month PPR | [10 empty] | 0% | 0%
| #2 | 1 Year PPR | [10 empty] | 0%
| #3 | Audit (due 6 months after end of fiscal year) | [10 empty] | 0%
| #4 | Annual Work Plan and Budget | [10 empty] | 0%
| #5 | [Activity, add aditional lines as needed] | [10 empty] | 0%
| #6 | [output tracking] | [8 empty] | Output indicator, if applicable |  | 0%
B. Project Management Costs
Office and field running costs
Project Management Unit: | #1 | Kickoff Workshop | [10 empty] | 0% | 0%
| #2 | Steering Committee Meetings | [10 empty] | 0%
| #3 | [Activity] | [10 empty] | 0%
| #4 | [Activity, add aditional lines as needed] | [10 empty] | 0%
Capital Assets
GRAND TOTAL (A+B) |  |  |  | YR 1: |  |  |  | 50000000
|  |  |  | Carry-over total (unspent funds from previous year) |  |  |  | 20000000 |  |  |  | % achieved for activities overall | 0.029412
|  |  |  | Request of funds for Upcoming Project Year |  |  |  | 30000000 |  |  |  | Actual budget for previous project year |  |  | 0

## Results Framework
Please adjust as needed (add outcomes, components, indicators, etc)
RESULTS FRAMEWORK
OUTCOME | INDICATOR | DEFINITION | METHOD | WHO | DISSAGREGATION | BASELINE | YR1 |  |  | YR2 |  |  | YR3 |  |  | YR4 |  |  | NOTES | Assumptions
[7 empty] | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved
Project Objective: [insert objective]
| [objective level indicator] | [5 empty] | 1 | 1 | 100% |  |  | 0% |  |  | 0% |  |  | 0%
| [objective level indicator] | [7 empty] | #DIV/0! |  |  | 0% |  |  | 0% |  |  | 0%
| GEF Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | Direct beneficiary: individuals receiving targeted support from the project. Targeted support: participation in working groups Indicator cumulative | See Appendix M (tally from activities in workplan) | PMU | Women | 0 |  |  | #DIV/0! |  |  | 0% |  |  | 0% |  |  | 0%
[5 empty] | Men | 0 |  |  | #DIV/0! |  |  | 0% |  |  | 0% |  |  | 0%
[5 empty] | Total | 0 |  |  | #DIV/0! |  |  | 0% |  |  | 0% |  |  | 0%
Project Objective achievement: | [8 empty] | #DIV/0! |  |  | 0% |  |  | 0% |  |  | 0%
Component 1: [insert component]
1.1. [insert outcome] | [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Component 1 achievement: | [8 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Component 2: [insert component]
2.1 [insert outcome] | [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
2.2 [insert outcome] | [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Component 2 achievement: | [8 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Component 3: [insert component]
3.1 [insert outcome] | [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
3.2 [insert outcome] | [insert indicator] | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Component 3 achievement: | [8 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
[6 empty] | Total % achieved |  |  | #NAME? |  |  | #NAME? |  |  | #NAME? |  |  | #NAME?

## Full Project Workplan
Project: [Add project title]
Period: Year X (dates)
FULL PROJECT WORKPLAN
Component | Outcome | Output | Activity # | Activities | Unit Description | End of Project Target | Who | Timeline |  |  |  | Budget (at activity, output, or outcome level)
[8 empty] | Y1 | Y2 | Y3 | Y4
0